## Sheet1
| Project Leadership |  |  |  |  | Project Team Members |  |  |  | Project Sub-Teams |  |  |  |  | External Resources
| Project Sponsor | Procurement Directors | Change Board | Steering Committee | Program Manager | Project Managers | Tech Lead | Functional Lead | Project Team Members | ESB Developers | Systems Engineers | Business Analyst | SecurIty Architect | 3rd Parties Vendors | IBM Project Manager | IBM Technical Lead | IBM Project Auditor
Initiate Phase Activities
- Letter of Award | I | R/A |  | I | I | I | I | I | I | I | I | I | I |  | C | C | I
- Contract Signatures and Sign Off | I | R/A | I | I | I | I | C | I | I | I | I | I | I | I | I | I | I
- Project Statement of Work | I |  | I | I | A | R | C | C | C | C | I | C | C | C | C | C | C
- Project Kick Off Meeting | C | C | I | C | A | A | I | I | I | I | I | I | I | I | C | I | I
- Stake Holder Register | C | C | bar: I to C
- Project Initiation Documents | C | C | I | C | A | R | I | I | I | I | I | I | I |  | C | I | I
- BRS Document Review | C | C | I | C | C | A | C | C | I | C | C | R | C | I | R | C | C
- Project Plan | I | A | I | I | C | R | C | C | I | I | I | C | C | C | C | C
Planning Phase Activities
- Business Requirements Gathering | I | I | C | I | I | A | C | C | I | I | I | R | I | C | C | C | C
- Technical Requirements Gathering | I | I | I | I | I | A | R | R | C | C | C | C | C | C | R | C | C
- Solution Description Document | I | I | I | I | I | A | R | R | C | C | C | C | C | C | R | C | C
- Business Change Management | I | I | A | I | C | R | C | C | I | I | I | I | I | C | C | C | C
- Environment Acceptance Criteria Documents | I | I | I | I | I | A | I | R | I | I | R | C | C | C | C | C | C
- RFP Specifications Acceptance Criteria Documents | C | A | I | C | R | R | I | I | I | I | I | I | I | I | C | I | I
- Training Plans and Registers | I | I | I | I | C | A | I | I | I | I | I | I | I | R | C | I | I
- Project Scope Baseline Sign Off | I | I | I | C | A | R | C | C | C | C | C | C | C | C | C | C | C
- Migration Plan | C | I | C | C | A | R | C | C | C | I | I | I | C | C | C | C | C
- Testing Plan | I | I | C | I | C | R | C | A | I | I | I | C | C | I | C | C | C
- Systems Specifications Document | I | I | I | I | C | A | C | C | C | I | I | R | I | I | C | I | I
- RACI Matrix | I | I | I | I | A | R | C | C | C | I | I | I | I | I | C | I | I
- Data Gathering Sheets | I | I | I | I | A | R | C | C | C | C | C | C | C | C | C | C | C
Execute Phase Activities
- Virtual environment server setup | I | I | I | I | I | A | R | C | I | I | R | I | R | R | I | R | I
- Design Message Flows | I | I | I | I | I | A | I | I | I | R | C | I | C | C | C | R | I
- Design Interfaces and Secure Platforms | I | I | I | I | I | A | I | I | I | R | C | I | C | C | C | R | I
- Training Registers | I | I | I | I | I | A | C | I | I | I | I | I | I | R | C | C | I
- Training Assessment Surveys | I | I | I | I | I | C | I | I | R | I | I | I | I | A | I | I | I
- Migration to Production implementation | I | I | C | C | C | A | R | C | C | C | R | C | C | C | C | R | C
- Business Change Management | C | C | A | C | C | R | I | I | I | I | I | I | I | C | C | I | C
- Handover to Owners | C | C | A | C | A | R | I | I | I | I | I | I | I | I | C | I | C
Control Phase Activities
- Review Project Scope Baseline | I | I | I | I | A | R | C | I | I | I | I | I | I | I | C | I | I
- Review Project Plan | I | I | I | I | A | R | C | I | I | I | I | I | I | I | C | I | I
- Review Deliverables | I | I | I | I | A | R | C | I | I | I | I | I | I | I | C | I | I
- Change Management | I | I | R | C | C | A | I | I | I | I | I | I | I | I | I | I | I
- RISK Management Plan | C | C | C | C | A | R | I | I | I | I | I | I | I | I | C | I | I
- Reporting Channels | C | I | I | I | C | R/A | I | I | I | I | I | I | I | I | I | I | I
Close Phase Activities
- Issue Acceptance test certificate | I | I | I | I | C | R | I | I | I | I | I | C | I | I | I | I | A
- Close vendor contracts | C | R | I | C | C | A | I | I | I | I | I | I | I | I | C | I | I
- Handover Document | C | C | I | I | A | R | I | I | I | I | I | I | I | I | C | I | I
- Closure Report | C | C | I | C | A | R | I | I | I | I | I | I | I | I | C | I | I
.
Role
Project Deliverable
(or Activity)